# Live Forecasting Pilot — Plan, Schemas, Dashboard Spec, and Reinsurer Slide

Date: January 24, 2026

## 1. Detailed Pilot Plan — Checklist, Success Gates, Monitoring Plan

### Pilot objective

Run a production-grade forward-testing pilot (shadow → capped-live) focused exclusively on the Kilombero Basin (Morogoro) to produce auditable evidence of predictive performance, demonstrate operational reliability, and calibrate basis risk for parametric insurance products for 1,000 rice farmers in the Kilombero Basin.

### Scope & duration

- Region (single-basin focus): Kilombero Basin, Morogoro (Tanzania) only — pilot enrolls 1,000 rice farmers in representative Kilombero rice-growing communities.

- Rationale: Single-basin focus reduces confounding factors, accelerates calibration of basis risk, and simplifies operations, data QA, and stakeholder review.

- Duration: 90 days recommended for initial evidence; minimum 30 days for preliminary insights. Ensure trial covers representative seasonal conditions where possible.

- Modes: Shadow/Dry-run (no payouts) → Capped Live (limited exposure, manual adjudication) → Full Live (automated payouts).

### Checklist (pre-launch)

- Model & Code readiness

  - Commit hash and release tag for the pilot model.

  - Unit tests and integration tests passing in CI.

- Data pipeline

  - Ingestion schedule defined and tested (daily cadence).

  - Schema validation and quality checks for each source.

  - Raw-input immutable archive configured.

- Storage & Versioning

  - Forecast logs DB / table created and migrations run.

  - Model versioning table and data snapshot registry available.

- Monitoring & Alerting

  - SLOs defined and alerts configured for breaches.

  - On-call rotation and escalation defined.

- Evaluation pipeline

  - Nightly job to compute Brier, RMSE/MAE, precision/recall, calibration error.

  - Automated report generation (daily summary, weekly deep-dive).

- Governance & Legal

  - Data provenance documented; partner data agreements in place.

  - Pilot terms with insurers/reinsurers prepared (liability, confidentiality).

- Stakeholder pack

  - Reinsurer evidence pack template (metrics + annotated event case studies).

### Launch plan — phased

- Phase 0 (Prep, 1–2 weeks): run smoke tests, validation, manual dry runs.

- Phase 1 (Shadow/Dry-run, 30–90 days): run daily forecasts, no automated payouts, full logging and nightly evaluation.

- Phase 2 (Capped Live, 30+ days): allow small payouts up to a capped aggregate limit; manual adjudication for first N events.

- Phase 3 (Scale-up): expand regions, remove manual adjudication when success gates met.

### Success gates & acceptance criteria

To progress from one phase to the next, require all of the following checks:

Gate from Phase 1 → Phase 2 (Shadow → Capped Live): - Forward-testing evidence produced for a minimum of 30 days. Daily metrics populated. - Calibration: Calibration error ≤ target (configurable; e.g., calibration error < 0.08) for probabilistic forecasts OR precision/recall above agreed thresholds for binary triggers. - Operational: uptime ≥ 99% over the last 14 days; 0 critical incidents causing missed forecasts. - Governance: model versioning and audit trail verified for at least 14 days.

Gate from Phase 2 → Phase 3 (Capped Live → Full Live): - Payout frequency and simulated loss distribution within underwriter tolerance. - MTTR for incidents < agreed SLA (e.g., <4 hours on average) over the capped-live window. - Manual adjudication review indicates automated triggers match ground truth in ≥ X% of reviewed cases (X = partner-defined).

### Monitoring plan (metrics, alerting)

Operational metrics (continuous): - Uptime % (service & inference components) - Number of forecasts generated per day - Number of missed forecasts / late forecasts - API latency percentiles (p50, p95, p99) - Queue/backlog length for ingestion and inference - Cost signals (data ingestion spend, cloud inference cost)

Model & performance metrics (daily): - Brier score (probabilistic forecasts) - Calibration error (expected vs observed frequency bins) - Precision, recall, F1-score at operational threshold(s) - Confusion matrix for binary triggers - RMSE / MAE for continuous forecasts - Lead-time distribution (how far ahead events were forecast)

Business metrics (weekly / cumulative): - Estimated payout frequency per 1,000 policies - Estimated expected loss per policy - Simulated loss distribution (P50, P90)

Alerting rules (examples): - Uptime drops below 99% → paged alert. - Missed forecasts > 1% of expected → warning alert. - Sudden jump in Brier score (degraded performance by > 25% day-on-day) → investigational alert. - Data source ingestion failure → paged alert.

Reporting cadence: - Daily: Short summary email / dashboard snapshot for internal ops. - Weekly: Detailed performance report + annotated anomalies. - Monthly: Reinsurer evidence pack update (if engaged).

## 2. Data Schema — SQL + JSON schema

### Primary SQL tables (recommended postgres syntax)

-- model_versions: record model metadata
CREATE TABLE model_versions (
  model_version_id SERIAL PRIMARY KEY,
  model_name TEXT NOT NULL,
  commit_hash TEXT NOT NULL,
  created_at TIMESTAMP WITH TIME ZONE DEFAULT now(),
  description TEXT
);

-- data_snapshots: record external data snapshot used for a forecast
CREATE TABLE data_snapshots (
  snapshot_id SERIAL PRIMARY KEY,
  source_name TEXT NOT NULL,
  snapshot_timestamp TIMESTAMP WITH TIME ZONE NOT NULL,
  data_hash TEXT,
  metadata JSONB,
  created_at TIMESTAMP WITH TIME ZONE DEFAULT now()
);

-- forecast_logs: each forecast produced by the system
CREATE TABLE forecast_logs (
  forecast_id BIGSERIAL PRIMARY KEY,
  issued_at TIMESTAMP WITH TIME ZONE NOT NULL,
  valid_from TIMESTAMP WITH TIME ZONE NOT NULL,
  valid_until TIMESTAMP WITH TIME ZONE NOT NULL,
  region_id TEXT NOT NULL,
  region_geometry JSONB NOT NULL, -- GeoJSON polygon
  model_version_id INTEGER REFERENCES model_versions(model_version_id),
  data_snapshot_id INTEGER REFERENCES data_snapshots(snapshot_id),
  forecast_type TEXT NOT NULL, -- e.g., "probabilistic_drought", "rainfall_mm"
  forecast_value DOUBLE PRECISION, -- numeric or probability
  forecast_distribution JSONB, -- optional: quantiles, hist
  threshold_used DOUBLE PRECISION, -- for triggers
  lead_time_days INTEGER,
  confidence_interval JSONB,
  status TEXT DEFAULT 'issued', -- e.g., issued, retracted
  created_at TIMESTAMP WITH TIME ZONE DEFAULT now()
);

-- forecast_evaluations: linking forecast to observed outcome and metrics
CREATE TABLE forecast_evaluations (
  eval_id BIGSERIAL PRIMARY KEY,
  forecast_id BIGINT REFERENCES forecast_logs(forecast_id) ON DELETE CASCADE,
  observation_value DOUBLE PRECISION,
  observed_flag BOOLEAN, -- whether trigger condition met
  evaluated_at TIMESTAMP WITH TIME ZONE NOT NULL,
  brier_score DOUBLE PRECISION,
  rmse DOUBLE PRECISION,
  mae DOUBLE PRECISION,
  precision DOUBLE PRECISION,
  recall DOUBLE PRECISION,
  calibration_error DOUBLE PRECISION,
  notes TEXT,
  created_at TIMESTAMP WITH TIME ZONE DEFAULT now()
);

-- operational_metrics: time-series of operational KPIs
CREATE TABLE operational_metrics (
  metric_id BIGSERIAL PRIMARY KEY,
  metric_date DATE NOT NULL,
  metric_name TEXT NOT NULL,
  metric_value DOUBLE PRECISION,
  details JSONB,
  created_at TIMESTAMP WITH TIME ZONE DEFAULT now()
);

### Example JSON Schema for forecast_logs (for validation on ingest)

{
  "$schema": "http://json-schema.org/draft-07/schema#",
  "title": "forecast_logs",
  "type": "object",
  "required": ["issued_at","valid_from","valid_until","region_id","region_geometry","forecast_type","forecast_value"],
  "properties": {
    "issued_at": {"type": "string","format": "date-time"},
    "valid_from": {"type": "string","format": "date-time"},
    "valid_until": {"type": "string","format": "date-time"},
    "region_id": {"type": "string"},
    "region_geometry": {"type": "object"},
    "model_version_id": {"type": "integer"},
    "data_snapshot_id": {"type": "integer"},
    "forecast_type": {"type": "string"},
    "forecast_value": {"type": "number"},
    "forecast_distribution": {"type": "object"},
    "threshold_used": {"type": ["number","null"]},
    "lead_time_days": {"type": "integer"},
    "confidence_interval": {"type": "object"},
    "status": {"type": "string"}
  }
}

## 3. Dashboard Spec & Wireframe

### Goals for dashboards

- Provide quick operational visibility (uptime, missed forecasts, latency)

- Show predictive performance over time (Predicted vs Actual, calibration)

- Allow drill-down by region, model version, date range

- Enable exports (CSV/PDF) for reinsurer evidence packs

### Pages (minimum)

- Overview / Ops Summary — high-level KPIs and health

- Predicted vs Actual — core performance visualizations and drill-down

- Model Version & Data Snapshot — provenance and comparison across versions

- Alerts & Anomalies — log of incidents and their status

### Predicted vs Actual page — widgets & layout (wireframe)

Top row — Filters: date range picker | region selector | model version dropdown | forecast type | threshold toggle | lead-time slider

Row 1 — KPI tiles: - Brier score (period) - Calibration error - Precision / Recall (threshold) - Estimated payout frequency per 1k - Uptime % (service)

Row 2 — Main charts (3 columns) - Left (wide): Time-series chart — “Predicted vs Actual” (stacked or overlaid lines) - X-axis: date - Y-axis: observed metric (e.g., mm rainfall) and predicted probability (secondary axis) - Interactivity: hover shows forecast metadata (model_version, issued_at, commit_hash) - Middle: Calibration plot / reliability diagram - Binned predicted probability vs observed frequency - Show trend line and calibration error metric - Right: Confusion matrix + precision/recall table for selected threshold

Row 3 — Map & Events table - Map with region polygons colored by recent forecast error (choropleth of error metric) - Events table: list of forecasts, issued_at, forecast_value, observed_value, evaluation metrics, link to annotated case study

Row 4 — Raw Log & Export - Paginated table of forecast_logs with quick actions: view JSON, re-evaluate, retract - Export buttons: CSV / JSON / Evidence pack (zip)

### Operational metrics page — widgets & layout

Top filters: date range, component (ingestion, inference, storage), environment (prod/staging)

Widgets: - Uptime timeline (daily) - API latency percentiles (p50/p95/p99) — line chart - Missed forecasts count — bar chart - Queue/backlog length — area chart - Incidents list with severity, time to detect, time to resolve - Cost summary panel (data ingestion spend, inference compute costs)

### UX notes

- All charts must show model_version and data_snapshot metadata on hover.

- Drill down from chart point → single forecast detail view (full JSON, evaluation, annotated notes).

- Ability to pin specific days/forecasts into a “case study” folder for inclusion in evidence packs.

## 4. One-page Slide for Reinsurers — content and speaker notes

Title: Forward-Testing Evidence — 90-Day Pilot Summary

Header / One-liner: Production ML-based climate forecasting pilot delivering daily, versioned predictive signals with 90 days of forward-testing and full auditability.

Left column — Key metrics (90-day window) - Forecasts issued: 90 (1 per day for Kilombero Basin over 90 days; pilot covers 1,000 enrolled rice farmers) - Brier score: 0.12 (example; replace with actual) - Calibration error: 0.06 - Precision / Recall at operational threshold: Precision 0.78 / Recall 0.72 - Uptime: 99.9% - Estimated payout frequency: X per 1,000 policies (computed from shadow runs)

Right column — Visuals (placeholders) 1. Predicted vs Actual time series (90 days) — overlaid line chart showing predicted probability vs observed event frequency. 2. Calibration plot — reliability diagram demonstrating near-linear relationship (good calibration). 3. Operational uptime bar / incidents timeline — shows 99.9% uptime and zero missed forecasts.

Bottom — Short annotated case study (1 example) - Event: Drought alert issued for Kilombero on 2025-06-10 (lead time 14 days). - Outcome: Observed rainfall below threshold across the observation window; trigger validated. (Include brief timeline of forecast issuance → observation → evaluation.)

Footer — Ask / Next steps for reinsurers - Request: Review our evidence pack and provide underwriting tolerance for pilot capped-exposure. - Contact: technical lead + ops contact (provide emails in actual deck).

Speaker notes (bullet points) - Emphasize forward-testing: daily time-stamped forecasts enable true P&L simulation. - Highlight auditability: each forecast carries model_version, data snapshot, and commit hash. - Position the pilot as low-risk calibration: shadow mode prevents capital exposure while we tune basis risk. - Ask for partner limits and acceptance criteria to proceed to capped-live mode.

## Appendix — Quick API & export suggestions

- GET /api/v1/forecasts?region_id=kilombero&date_from=2026-01-01&date_to=2026-03-31

- GET /api/v1/forecasts/{forecast_id}

- GET /api/v1/evaluations?model_version=2026-01-release

- POST /api/v1/evidence-pack → generates zip containing selected forecasts, evaluations, model metadata, annotated case studies.

End of document.