# Shadow-Run Pilot Simulation: Rationale, Evaluation, and Execution Plan

Date: January 24, 2026

Purpose
This document consolidates the rationale, evaluation framework, and practical execution plan for running a shadow-run (no-payout) simulation of the Kilombero Basin pilot for 1,000 rice farmers. The goal is to produce forward-testing evidence, calibrate basis risk, and prove operational readiness before exposing capital.

Quick Evaluation (High Level)
- The core thesis is correct: forward-testing, basis risk calibration, operational reliability, and proprietary performance data are what turn a research prototype into an underwritable insurance system.
- What must be proven: reliability and predictive value under live conditions, plus demonstrable control of financial exposure.
- Main risk: short pilots can look good while hiding seasonal effects, corner cases, or pipeline fragility. Instrumentation and experiment design must be rigorous.

Why a Shadow-Run Simulation Makes Sense
- No capital at risk: you can measure false positives/negatives and payout frequency without paying anyone.
- Forward-testing produces real-world evidence: time-stamped forecasts compared to later observations.
- It reveals operational failure modes: data delays, API changes, pipeline bugs, and versioning issues.
- It enables product tuning: thresholds, lead times, and payout rules can be adjusted empirically.
- It builds a proprietary dataset: each forecast plus outcome becomes training and evidence data.

What “Doable” Means in Practice
You can run:
1) Hindcast simulation: replay historical timelines as if the system were live.
2) Live shadow run: run the real pipeline daily, store forecasts, do not pay.
3) Monte Carlo wrapper: stress-test payout distributions under uncertainty.

Key Outputs to Collect
For each forecast:
- issued_at, valid_from, valid_until, model_version, data_snapshot, forecast_value, threshold_used, lead_time_days, region_id.
For each evaluation:
- observed_value, observation_window, trigger flag, Brier score, RMSE/MAE, confusion matrix position.
Aggregates:
- Calibration curves, precision/recall, payout frequency per 1,000 policies, expected loss per policy, uptime and incident logs.

Concrete Simulation Recipe
1. Define policy attachment rules and payout structure.
2. Assemble historical or live observation feeds using the same pipeline.
3. Generate daily forecasts with full versioned metadata.
4. Convert probabilities to triggers using operational thresholds.
5. Link forecasts to observation windows and record outcomes.
6. Compute per-forecast metrics (Brier, RMSE/MAE, confusion matrix).
7. Compute business metrics (payout frequency, expected loss).
8. Run Monte Carlo or bootstrap to estimate tail risk.
9. Produce reports and an evidence pack.

Suggested Acceptance Criteria
- Calibration error within agreed bounds (e.g., < 0.08).
- Precision or recall around or above 0.7 depending on risk appetite.
- Uptime >= 99% during shadow run.
- Zero missed critical forecasts.
- Payout frequency within underwriter tolerance.

Technical Caveats
- Hindcast is not sufficient alone: simulate data latency and imperfections.
- Satellite observations are imperfect proxies for on-the-ground reality.
- Exposure modeling must reflect whether triggers pay all 1,000 farmers or subsets.
- Seasonality matters: short windows can mislead.
- Always version models and data snapshots.

Example Expected Loss Calculation
If annual trigger probability is p and payout per farmer is A, expected loss per farmer per year is p × A. For 1,000 farmers, total expected annual loss is 1,000 × p × A.

Conclusion
Running a shadow-run simulation is the correct, industry-standard step to convert your system from a prototype into an underwritable product. It produces evidence, calibrates risk, and hardens operations without risking capital.